## Slide 1: Chemistry careers in SMEs
Introduction to project management
Samantha Pugh
University of Leeds

## Slide 2: What is project management?
How would you define project management?
Dr Simon Pugh, Project Dexterity Ltd
Project management consultant
Notes: Ask students in pairs to define what they think project management is about. Collect answers from the class after a couple of minutes.
Generally, students will reply with the “hard skills”. Use the video to give an expert opinion on what constitutes project management.

## Slide 3: Project management skills 1
Planning software
Technical requirements
Business processes
Time management
Risk management
Budgeting
Resource planning
Hard skills

## Slide 4: Project management skills 2
Soft skills
Relationship building
Communication
Influencing
Leadership
Problem solving

## Slide 5: Stakeholder engagement
Who are the key stakeholders for your project?
  Staff
  Other students
  Wider community?
How will you consult them?
How will you seek their support or endorsement?
Who influences the outcome of your project?
Notes: Emphasise the importance of winning support for your project. The key to this is good communication, and recognising the different levels of communication that are required for the different stakeholders.

## Slide 6: Project management principles
A project is a temporary organisation
A project is based on deliverables
Product-based management
Manage by exception
Manage and plan in stages
A project must have a continued business justification
Notes: Note that for a business, if a project no longer has a business case then it should be aborted. This should not be seen as a failure, as long as lessons are learned and noted for future work.

## Slide 7: Project management tools
PRINCE2™ project management system
Project specification
Product breakdown structure
Timescales and pert charts
Gantt charts
Risk analysis
Notes: The tools shouldn’t be introduced here, because they are going to be discussed in the next few slides. These are all industry standard tools though, and students gaining an understanding of them at this stage will be useful when they go to interviews.

## Slide 8: PRINCE2™
A stage-gate process
Manage in stages
  Review the business case before moving onto the next stage
Manage by exception
  Set the parameters for acceptability
  Only seek project board approval for off-specifications
Notes: Note that PRINCE2 is used widely in some sectors such as public health and IT. It is possible to study PRINCE2 to become a qualified PRINCE2 Practitioner.
The key point here is not PRINCE2 per se, but that it is a stage-gate process. Stage-gate processes are often used in R & D environments, so understanding the basic principles will be useful for anyone wanting a career in product development.

## Slide 9: Project specification
Before embarking on a project, you need to define a shared vision for the project.
What and Why
When
How
Who
What success will look like?
Ensure stakeholder buy-in
Notes: This is self-explanatory, but I would emphasise the need for all members of the team to define the project, and know what success will look like, i.e. what are they trying to achieve?

## Slide 10: Product breakdown structure
Consider your project outputs as a range of products or deliverables
You can then manage each of these “products”
Each product needs a specification – what will success look like?
Then you can consider how they link to each other
Notes: Encourage students to focus on what they are trying to produce to specify their project, rather than focussing on what they have to do. Makes it easier to plan.

## Slide 11: PERT charts
Notes: Define each of the project outputs, and then a PERT chart can be used to show how each of the tasks link to each other. Useful for showing interdependencies. This also helps to show what tasks can be done in parallel and what needs to be done sequentially.

## Slide 12: Gantt charts
Gantt Charts are useful for seeing timeline interdependencies of products
Some aspects of a project cannot be started until a preceding event is completed.
Gantt Charts provide the critical path for the project.

## Slide 13: Gantt chart 1
Clearly shows
When activities start and finish
Where a project should be at a given time
Which activities are parallel
Critical Paths

## Slide 14: Gantt chart 2
Makes it easier to
Plan
Allocate resources
Check if on schedule

## Slide 15: Mind maps 1
Effective in the early stages of a project
Memory aid or information organiser
Also useful for stimulating creativity

## Slide 16: Mind maps 2
How to make a mind map
http://bit.ly/1Bp4QtL

## Slide 17: Activity
You are going to organise the university graduation ball
Notes: This should be a fun activity – you can replace with any suitable event that you think students would be able to apply a “common sense” approach to.

## Slide 18: Task 1
In your group
Produce a mind map for the preparation and the event
5 minutes
Notes: Tell the students to brainstorm ideas and capture everything. They don’t need to evaluate the merits of the ideas at this stage.

## Slide 19: Task 2
Drill down and specify the components of your “project”
What’s your timeline?
10 minutes
Notes: It is useful to get the students to write each of the tasks onto post-it notes, so that they can be rearranged into their interdependencies in task 3.

## Slide 20: Task 3
For the tasks you have listed rearrange them to reflect the various interdependencies of your tasks
5 minutes
Notes: The point from this part of the activity that as a group they can distribute tasks, which means tasks can be completed in parallel, although they should also see where the critical points are in the project and what forms the critical path.

## Slide 21: Task 4
Draw up a plan for the first stage
What will success look like?
What will be essential to pass through the “gate” to the next stage?

## Slide 22: Risk
Risk analysis should be done at all stages of a project
Anticipate what may go wrong to try to minimise problems
Based on known risks and previous experience
Risk = Probability × Impact
Notes: Students will be familiar with risk in the context of practical risk assessments. Therefore you can encourage them to apply these principles to looking for risk in a project. However, it should be pointed out that these are business risks, rather than safety risks.

## Slide 23: Risk management strategy
Identify
Assess (estimate and evaluate)
Plan
Implement
Communicate

## Slide 24: Strategies for dealing with risk
Avoid
Fall-back/contingency
Transfer
Accept

## Slide 25: For your group project
What is your project about?
What are the first stage tasks?
Who are your stakeholders?
Think about managing by exception
Do you have a shared vision for your project?

## Slide 26: Summary
You should now have some project management tools and strategies to help you with your tasks for this module.

## Slide 27: Copyright information
This resource “new name”, is a derivative of “RSC project management” by The Royal Society of Chemistry used under CC-BY-NC-SA 4.0. “new name” is licensed under CC-BY-NC-SA 4.0 by “name of user”.